## Sheet1
Task Name | Duration | Start | Finish
1.Initiation | 15 days | Tue 6/1/21 | Mon 6/16/21
1.1 Onboard Stakeholders | 4 days | Tue 6/1/21 | Thu 6/4/21
1.2 Discuss and Prepare Project Charter | 5 days | Fri 6/5/21 | Wed 6/9/21
1.3 Review the project charter by PM and Client | 3 days | Thu 6/10/21 | Fri 6/12/21
1.4 Project charter signed/approved | 2 day | Mon 6/13/21 | Mon 6/15/21
1.5 Evaluations and recommendations | 1 days | Mon 6/16/21 | Mon 6/16/21
2.Planning | 37 days | Tue 6/17/21 | Fri 7/25/21
2.1 Prepare primary scope | 4 days | Tue 6/17/21 | Thu 6/20/21
2.2 Determine and Onboard the team members | 6 days | Fri 6/21/21 | Thu 6/27/21
2.3 Project team kick-off meeting | 2 day | Fri 6/28/21 | Fri 6/30/21
2.4 Develop project requirements | 7 days | Mon 07/1/21 | Mon 7/7/21
2.5 Develop project plan | 5 days | Tue 7/8/21 | Fri 7/12/21
2.6 prepare project cost plan | 8 days | Mon 7/13/21 | Tue 7/19/21
2.7 prepare time management plan | 4 days | Wed 7/20/21 | Fri 7/23/21
2.8 Review prepared plans with client | 1 days | Fri 7/24/21 | Fri 7/24/21
3.Execution | 74 days | Mon 7/25/21 | Fri 10/08/21
3.1 Conduct a requirement meeting and find Requirements | 8 days | Mon 7/25/21 | Tue 8/1/21
3.2 Determine required software | 5 days | Wed 8/2/21 | Mon 8/6/21
3.3 Up and run the systems with required software | 15 days | Tue 8/7/21 | Fri 8/21/21
3.4 Determine required hardware servers | 15 days | Mon 8/22/21 | Thu 9/6/21
3.5 Backup existing server files and server settings | 9 days | Fri 9/7/21 | Tue 9/15/21
3.5 Install new servers | 11 days | Wed 9/16/21 | Tue 9/26/21
3.6 Restore backed up servers | 6 days | Wed 9/27/21 | Tue 10/3/21
3.7 Update Systems | 4 days | Wed 10/4/21 | Fri 10/7/21
3.8 Execution Complete | 1 days | Fri 10/8/21 | Fri 10/8/21
4.Monitoring and Controlling | 14 days | Mon 10/9/21 | Fri 10/23/21
4.1 Test the build system time to time | 4 days | Mon 10/9/21 | Wed 10/13/21
4.2 Test the performance | 5 days | Thu 10/14/21 | Tue 10/19/21
4.3 Prepare the performance evaluation report | 4 days | Wed 10/20/21 | Fri 10/23/21
5. Closing | 4 days | Mon 10/24/21 | Tue 10/27/21
5.1 conduct a retrospective meeting and review | 3 days | Mon 10/24/21 | Tue 11/26/21
5.2 Project Completion | 1 days | Tue 10/26/21 | Tue 10/27/21